## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10hrs / week) | [6 empty] | Week #4 (10 hrs / week) | [6 empty] | Week #5 (10 hrs / week) | [6 empty] | Week #6 (10 hrs / week) | [6 empty] | Week #7 (10 hrs / week) | [6 empty] | Week #8 (10 hrs / week) | [6 empty] | Week #9 (10 hrs / week) | [6 empty] | Week #10 (10 hrs / week) | [6 empty] | Week #11 (10 hrs / week)
Backlog Item | Task Distribution | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 11) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75 | D76 | D77
 | time axis 2023-02-19 to 2023-05-06
|  |  | Ideal Trend | 440 | 434 | 428 | 422 | 416 | 410 | 404 | 398 | 392 | 386 | 380 | 374 | 368 | 362 | 356 | 350 | 346 | 344 | 342 | 338 | 332 | 326 | 320 | 314 | 308 | 302 | 296 | 294 | 290 | 284 | 278 | 272 | 266 | 260 | 254 | 248 | 242 | 236 | 230 | 224 | 218 | 212 | 206 | 200 | 194 | 188 | 182 | 176 | 170 | 164 | 158 | 152 | 146 | 140 | 134 | 128 | 122 | 116 | 110 | 104 | 98 | 92 | 86 | 80 | 74 | 68 | 62 | 56 | 50 | 44 | 38 | 32 | 26 | 20 | 14 | 8 | 2
|  |  | Remaining Effort (440 hrs) | 440 | 436 | 430 | 422 | 415 | 408 | 402 | 402 | 397 | 388 | 380 | 372 | 367 | 360 | 360 | 355 | 349 | 342 | 333 | 327 | 321 | 321 | 315 | 310 | 302 | 295 | 287 | 278 | 278 | 276 | 269 | 260 | 252 | 248 | 240 | 238 | 238 | 238 | 238 | 238 | 238 | 230 | 217 | 210 | 202 | 195 | 185 | 172 | 165 | 158 | 154 | 149 | 143 | 139 | 132 | 127 | 119 | 110 | 101 | 95 | 90 | 86 | 83 | 79 | 72 | 66 | 56 | 47 | 38 | 31 | 21 | 11 | 2 | 0 | 0 | 0 | 0
| Integration of UI and Backend | Mounish | 110 | 110 | 108 | 107 | 105 | 103 | 102 | 100 | 100 | 98 | 97 | 96 | 94 | 93 | 90 | 90 | 88 | 87 | 85 | 83 | 81 | 79 | 79 | 78 | 77 | 75 | 75 | 73 | 70 | 70 | 69 | 67 | 65 | 63 | 62 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 58 | 55 | 53 | 52 | 50 | 47 | 44 | 43 | 41 | 40 | 39 | 37 | 36 | 34 | 32 | 30 | 28 | 25 | 23 | 21 | 20 | 20 | 19 | 17 | 15 | 12 | 9 | 9 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Lohith | 110 | 110 | 109 | 108 | 106 | 104 | 102 | 101 | 101 | 99 | 97 | 95 | 93 | 92 | 90 | 90 | 89 | 87 | 85 | 83 | 82 | 81 | 81 | 79 | 77 | 75 | 72 | 70 | 68 | 68 | 68 | 66 | 64 | 61 | 60 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 56 | 52 | 51 | 49 | 47 | 44 | 40 | 38 | 37 | 36 | 34 | 32 | 32 | 30 | 30 | 28 | 26 | 24 | 23 | 22 | 21 | 21 | 20 | 18 | 18 | 15 | 13 | 10 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0
| Implement Back-End Code | Shlok | 110 | 110 | 109 | 107 | 105 | 104 | 102 | 100 | 100 | 99 | 97 | 95 | 93 | 91 | 90 | 90 | 88 | 87 | 86 | 83 | 82 | 81 | 81 | 79 | 78 | 75 | 72 | 70 | 68 | 68 | 68 | 67 | 64 | 63 | 62 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 58 | 55 | 53 | 52 | 50 | 48 | 45 | 43 | 41 | 40 | 39 | 37 | 35 | 33 | 33 | 31 | 28 | 26 | 24 | 23 | 22 | 22 | 21 | 19 | 17 | 15 | 13 | 10 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Implement Back-End Code | Surya | 110 | 110 | 110 | 108 | 106 | 104 | 102 | 101 | 101 | 100 | 97 | 94 | 92 | 91 | 90 | 90 | 90 | 88 | 86 | 84 | 82 | 80 | 80 | 79 | 78 | 77 | 76 | 74 | 72 | 72 | 71 | 69 | 67 | 65 | 64 | 62 | 60 | 60 | 60 | 60 | 60 | 60 | 58 | 55 | 53 | 49 | 48 | 46 | 43 | 41 | 39 | 38 | 37 | 37 | 36 | 35 | 32 | 30 | 28 | 26 | 25 | 24 | 23 | 20 | 19 | 18 | 16 | 14 | 12 | 9 | 8 | 7 | 2 | 1 | 0 | 0 | 0 | 0
Team:
Mounish Juvvadi | 10 hours / Week
Lohith reddy K | 10 hours / Week
Shlok Patel | 10 hours / Week
Surya Teja Palle | 10 hours / Week
Total Available Hours During Sprint: | 40